## DPR
क्वार जल विद्युत परियोजना (540 मेगावाट)/ Kwar Hydroelectric Project (540 MW)
दैनिक प्रगति रिपोर्ट / Daily Progress Report
Date: | 21.08.2024
Activity Code | Area of Activity | Unit | Total Qty. | Actual date of start | Actual date of finish | Progress (upto last Month) | Monthly Target (July-24) | Monthly Progress | Days progress | Cumulative progress | Balance Qty. | %complete | Remarks
KW1-7 | Coffer Dams and River Diversion
Reconstruction of Coffer dam after monsoon
KW1-7.1 | Construction of Pre-Coffer Dam
KW1-7.2 | River Diversion | [11 empty] | River diverted on 15.01.2024
KW1-7.3 | Construction of Coffer Dams U/s & D/s including Grouting Works | cum | 61023 | 16-01-2024 |  | 61023 | 0 | 0 | 0 | 61023 | 0 | 100% | Coffer dam quantity is 61023 for year 2023-24. Coffer dam breached on 22.05.2024
KW1-7.4 | Reconstruction of Coffer Dam after Monsoon
KW1-7.5 | Reconstruction of Coffer Dam after Monsoon
KW1-8 | Concrete Gravity Dam
DAMSP110A | Tunnel Spillway 1(heading) stage:1 | Mtr | 456 | 17.08.2022 |  | 456 |  | 0 | 0 | 456 | 0 | 100% | Activity completed on 16.09.2023 | 1
DAMSP110A | Tunnel Spillway 1(heading) stage:2 | Mtr | 456 |  |  | 440 |  | 0 | 0 | 440 | 16 | 96.49% | Activity completed on 10.11.2023 | 0.96491
KW1-8.1 | Dismantling of Existing Suspension Footbridge over River Chenab at Dam axis | LS
KW1-8.2 | Construction of Internal Access Roads in Dam Body | LS |  | 01-12-2022
KW1-8.3 | Dam - Excavation - Stripping of Dam Abutments on Left Bank | cum | 169690 | 10-05-2023 |  | 150615 | 18000 | 9220 | 500 | 159835 | 9855 | 94.19% | Rock bolt- 9 nos.
KW1-8.4 | Dam - Excavation - Stripping of Dam Abutments on Right Bank | cum | 55000 | 01-07-2023 |  | 48020 | 5000 | 1890 | 100 | 49910 | 5090 | 90.75%
KW1-8.5 | Dam - Excavation Below River Bed | cum | 84000 | 15.02.2024 |  | 61099 | 0 | 0 | 0 | 61099 | 22901 | 72.74% | Excavation has been stopped due to breach of Coffer dam on 22.05.2024
KW1-8.6 | Dam - Foundation Treatment in Riverbed Portion for first block
KW1-8.7 | Dam - Concreting - Up to Crest level of Under sluice/ Construction sluices | cum | 135000
KW1-8.8 | Dam - Concreting - Up to Crest Level of Orifice Spillway | cum | 290000
KW1-8.9 | Dam - Concreting - Up to Crest Level of Crest Spillway | cum | 240000
KW1-8.10 | Dam - Concreting - Up to Top including all Piers & Bridge Deck | cum | 85000
KW1-8.11 | Dam - Control Room Works, Other Protection & Misc Ancillary Works
KW1-11 | Pressure Shaft
KW1-11.4 | Pressure Shafts / Penstock Excavation
KW1-11.4.1 | Pressure Shaft - Surface Excavation including erection platform
KW1-11.4.4 | Pressure Shaft No. 3
KW1-11.4.4.1 | Pressure Shaft No. 3: UG Excavation of Top Horizontal Limb | m | 25.87
KW1-11.4.4.2 | Pressure Shaft No. 3: UG Excavation of Vertical Potion Limb | m | 80.45 | 10-06-2024 |  | 5 | 0 | 0 |  | 5 | 75.45 | 6.215% | Erection of Gantry Crane is under progress.
KW1-11.4.4.3 | Pressure Shaft No. 3: UG Excavation of Bottom Horizontal Limb | m | 44.53
KW1-11.4.5 | Pressure Shaft No. 4
KW1-11.4.5.1 | Pressure Shaft No. 4: UG Excavation of Top Horizontal Limb | m | 19.7
KW1-11.4.5.2 | Pressure Shaft No. 4: UG Excavation of Vertical Potion Limb | m | 93.45 | 24-04-2024 |  | 5 | 0 | 0 |  | 5 | 88.45 | 5.35% | Erection of Gantry Crane is under progress.
KW1-11.4.5.3 | Pressure Shaft No. 4: UG Excavation of Bottom Horizontal Limb | m | 44.53
KW1-12 | Power House Complex
KW1-12.1 | Adits & Main Access tunnel (MAT) to Powerhouse
KW1-12.1.1 | Main Access Tunnel (MAT) - Access Road upto portal |  |  | 11-10-2022 | 25-10-2022 | [7 empty] | Completed on 25-10-2022
KW1-12.1.2 | Main Access Tunnel (MAT) - Portal Development | cum | 19000 | 27-10-2022 | 25-12-2022 | [7 empty] | Completed on 25-12-2022
KW1-12.1.3 | Main Access Tunnel (MAT) - UG Excavation upto Junction J1 | m | 225.57 | 26-12-2022 | 04-08-2023 | [7 empty] | Completed on 04-08-2023
KW1-12.1.4 | Main Access Tunnel (MAT) - UG Excavation From Junction J1 to Junction J2 | m | 156.25 | 05-08-2023 | 23-10-2023 | [7 empty] | Completed on 23-10-2023
KW1-12.1.5 | Main Access Tunnel (MAT) - UG Excavation From Junction J2 to Junction J3 | m | 93.11 | 24-10-2023 | 04-12-2023 | [7 empty] | Completed on 04-12-2023
KW1-12.1.6 | Main Access Tunnel- UG Excavation from Junction J3 to Power House (remaining) | m | 129.94 | 08-01-2024 | 30-05-2024 | [7 empty] | Completed on 30-05-2024
KW1-12.1.7 | Adit to Power House Crown - UG Excavation - taking off from MAT at J3 | m | 102.02 | 05-12-2023 | 03-01-2024 | [7 empty] | Completed on 03-01-2024
KW1-12.2 | Power House Excavation
KW1-12.2.1 | Power House Excavation | cum | 141000 | 45295 |  | 34418 | 5000 | 2000 | 0 | 36418 | 104582 | 25.83% | Heading excavation upto EL 1269 m is completed. -Benching work upto EL 1258.65m- Rockbolts -15 No.
KW1-12.2.1 | PH - Pilot Excavation | m | 140 | 04-01-2024 | 14-03-2024 | [7 empty] | Completed on 14-03-2024
KW1-12.2.2 | PH- Crown widening I.e EL 1274.15m | m | 140 | 08-02-2024 | 26-06-2024 | [7 empty] | Completed on 26-06-2024
KW1-12.2.3 | PH - Benching upto MAT Top Level i.e. EL 1267.15m | m | 7 | 27-06-2024
KW1-12.2.3 | PH - Benching upto MAT Top Level i.e. EL 1267.15m | Cum | 16800 | 27-06-2024 |  | 188 | 10000 | 3360 | 200 | 3548 | 13252 | 21.12% | Excavation from EL 1272 to 1270 m is under progress.
KW1-12.2.4 | PH - Benching upto MAT Level i.e. EL 1258.65m | m | 8.5
KW1-12.2.5 | PH - Benching upto Generator Floor Level i.e. EL 1253.35m | m | 5.3
KW1-12.2.6 | PH - Benching upto MIV Floor Level i.e. EL 1237.65m | m | 15.7
KW1-12.2.7 | PH - Draft tube Pit & Drainage Pit Excavation upto bottom i.e. EL 1230.75m | m | 6.9
KW1-12.2.8 | PH - Service Bay Raft, Beams, Columns concreting upto EOT | m | 11
KW1-12.2.9 | PH - Erection of EOT Crane in Service Bay - By E&M Agency
KW1-12.2.10 | PH - Concreting of Columns & Beams in Machine Hall upto EOT
KW1-12.2.11 | PH - Extension of EOT Crane over Machine Hall area of PH
KW1-13 | Transformer Hall (TC) & Access Tunnel (AT)
KW1-13.1 | Adit Cum Cable Tunnel (ACCT)
KW1-13.1.1 | ACCT - Portal Development | cum | 4700
KW1-13.1.2 | ACCT - UG Excavation upto GIS Cavern | m | 274.62 | 02-01-2023 | 18-09-2023 | [7 empty] | Completed on 18-09-2023
KW1-13.1.3 | ACCT - Extension inside GIS as Pilot Excavation | m | 65 | 19-09-2023 | 21-11-2023 | [7 empty] | Completed on 21-11-2023
KW1-13.1.4 | ACCT - Extension of ACCT from GIS cavern to TC | m | 15 | 22-11-2023 | 02-12-2023 | [7 empty] | Completed on 02-12-2023
KW1-13 | Transformer Cavern excavation | cum | 57000 | 2023-12-01 |  | 26340 | 3000 | 2750 | 150 | 29090 | 27910 | 51.04% | Heading excavation work upto EL 1317 m is Completed.⁠ SFRS -5 cum Rockbolt - 4nos.
KW1-13.2 | Access Tunnel to Transformer Cavern (ATTC)
KW1-13.2.1 | ATTC Excavation (J1) | m | 315 | 2023-08-07 |  | 283 | 20 | 32 | 0 | 315 | 0 | 100% | Rockbolt - 4nos.
KW1-13.2.1 | ATTC- UG Excavation upto Junction with Adit cum Surge Gallery for TRT-2 | m | 293 | [9 empty] | Rockbolt- 10 nos
KW1-13.2.2 | ATTC - UG Excavation from Adit cum Surge Gallery for TRT-2 to TC | m | 50
KW1-13.3 | Transformer Hall (TC)
KW1-13.3.1 | TC - Pilot Excavation | m | 116 | 03-12-2023 | 06-01-2024 | [7 empty] | Completed on 06-01-2024
KW1-13.3.2 | TC - Crown Widening | m | 116 | 07-01-2024 | 01-07-2024 | [7 empty] | Completed on 01-07-2024
KW1-13.3.3 | TC - Benching upto Floor Level (EL. 1310.0m) | m | 116 | 02-07-2024
KW1-13.3.3 | TC - Benching upto Floor Level (EL. 1310.0m) from SPL to El 1310 m | cum | 24474 | 07-01-2024 |  | 10264 | 5000 | 2900 | 200 | 13164 | 11310 | 53.79% | Benching excavation is under progress.
KW1-13.3.4 | TC - UG Excavation of Equipment Gallery | m | 26
KW1-13.3.5 | TC - Bottom Raft, Beams, Columns concreting upto Top | m | 26
KW1-13.3.6 | TC - UG Excavation of Cable Trench
KW1-16 | Tailrace Tunnels (TRTs)
KW1-16.1 | Adits to TRT & Adit cum Surge Gallery
KW1-16.1.1 | TRT-Access road to Adit taking off from Bridge at D/s of Dam |  |  | 11-10-2022 | 30-07-2023 | [7 empty] | Completed on 30-07-2023
KW1-16.1.2 | TRT Adit - Portal Development | cum | 4000 | 31-07-2023 | 17-08-2023 | [7 empty] | Completed on 17-08-2023
KW1-16.1.3 | D/S Surge Gallery For TRT-1 - Portal Development | cum | 2500 | 12-01-2023 | 12-02-2023 | [7 empty] | Completed on 12-02-2023
KW1-16.1.4 | TRT Adit - UG Excavation | m | 536 | 18-08-2023 |  | 453.4 | 25 | 21.5 | 0 | 474.9 | 61.1 | 88.6% | Rock support work in progress at Junction of Adit and TRT-2 Concrete laggings - 3 cum
KW1-16.1.5 | D/S Surge Gallery For TRT-1 - UG Excavation - Heading | m | 766 | 13-02-2023 |  | 654 | 60 | 31.5 | 2 | 685.5 | 80.5 | 89.49% | Rock support work Rockbolt - 0. SFRS- 0 cum, Ribs-0 MT Benching work under progress
KW1-16.1.6 | D/S Surge Gallery For TRT-1 - UG Excavation - Benching | m | 766 | 15-01-2024 |  | 431 | 40 | 28 | 20 | 459 | 307 | 59.92%
KW1-16.1.7 | Adit Cum Surge Gallery For TRT - 2 - UG Excavation - Heading | m | 775
KW1-16.1.8 | Adit Cum Surge Gallery For TRT - 2 - UG Excavation - Benching | m | 775
KW1-17 | Control Block Cavern
KW1-17.1 | Excavation of Control Block | cum | 17500 |  |  | 8599 | 3000 | 0 | 0 | 8599 | 8901 | 49.14% | Heading excavation work upto EL 1270 m is Completed
*Remarks - Labour was on strike for 6 hours in both day and night shift